## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: Thrust Vector Controlled Rocket
Hunter |  |  |  |  | Legend: | TVC Mount, Avionics Hardware, Static Fire | [19 empty] | RECO, Avionics Software, Stage 0 | [18 empty] | Structure, Controller, Launch
Rohovit
Project start date: | 2025-08-17 |  |  |  |  | August | [20 empty] | September | [27 empty] | October
Scrolling increment: | -1 | time axis 2025-08-16 to 2025-10-10
Column1 | Category | Status | Start | End | Days Left | time axis 2025-08-16 to 2025-10-10
Rocket Development
List Issues with Old TVC Mount | TVC Mount | Completed | 2025-08-17 | 2025-05-11 | -98
Calculate DOFs of mount | TVC Mount | Completed | 2025-08-17 | 2025-05-12 | -97
Calculate Shear Loads on Old Mount | TVC Mount | Completed | 2025-08-17 | 2025-05-12 | -97
Look at Servo Specs | TVC Mount | Completed | 2025-08-17 | 2025-05-12 | -97
Determine number of DOFs needed | TVC Mount | Completed | 2025-08-17 | 2025-05-12 | -97
Determine an ideal gear ratio | TVC Mount | Completed | 2025-08-17 | 2025-05-12 | -97
Quantify Rotation due to Servo rotation | TVC Mount | Completed | 2025-08-17 | 2025-05-12 | -97
Buy new Servos | TVC Mount | Completed | 2025-08-17 | 2025-05-12 | -97
Print TVC | TVC Mount | Completed | 2025-08-24 | 2025-05-19 | -90
V2 Mount 1 Print | TVC Mount | Completed | 2025-08-24 | 2025-05-19 | -90
Research Parachute Deploy Mechanism | RECO | Completed | 2025-05-19 | 2025-05-26 | -83
Determine Optimal CG Location | Structure | Completed | 2025-05-19 | 2025-05-26 | -83
Rocket CAD | Structure | Completed | 2025-05-19 | 2025-05-26 | -83
Determine Size of Parachute | RECO | Completed | 2025-05-19 | 2025-05-26 | -83
Determine Rocket Motors | TVC Mount | Completed | 2025-05-19 | 2025-05-26 | -83
Avionics Development
Determine Electronic Modules Needed | Hardware | Completed | 2025-08-24 | 2025-05-19 | -90
Determine Microcontroller(s) | Hardware | Completed | 2025-08-24 | 2025-05-19 | -90
Determine Wiring Layout | Hardware | Completed | 2025-08-24 | 2025-05-19 | -90
Buy Electronics Needed | Hardware | Completed | 2025-08-24 | 2025-05-19 | -90
Determine Electronics for RECO | Hardware | Completed | 2025-05-19 | 2025-05-26 | -83
Build Rocket Circuit | Hardware | Completed | 2025-05-26 | 2025-06-02 | -76
TVC Movement Code | Software | Completed | 2025-05-26 | 2025-06-02 | -76
IMU Collection Code | Software | Completed | 2025-05-26 | 2025-06-02 | -76
TVC Response to IMU Code | Software | Completed | 2025-05-26 | 2025-06-02 | -76
Telemetry Code | Software | In Progress | 2025-05-26 | 2025-06-02 | -76
Research Control Algorithms | Controller | In Progress | 2025-06-02 | 2025-06-09 | -69
Basic Control Algorithm 1 | Controller | In Progress | 2025-06-02 | 2025-06-09 | -69
Revised Control Algorithm 2 | Controller | Not Started | 2025-06-02 | 2025-06-09 | -69
TVC Response with Control Algorithm | Controller | Not Started | 2025-06-02 | 2025-06-09 | -69
Parachute Deploy Code | Software | Completed | 2025-06-02 | 2025-06-09 | -69
Flight Code 1 | Software | In Progress | 2025-06-09 | 2025-06-16 | -62
Simulation 1 | Software | In Progress | 2025-06-09 | 2025-06-16 | -62
Flight Code 2 | Software | Not Started | 2025-06-09 | 2025-06-16 | -62
Simulation 2 | Software | Not Started | 2025-06-09 | 2025-06-16 | -62
Testing/Launch Hardware
CAD for Static Gimbal Mount | Static Fire | Completed | 2025-05-26 | 2025-06-02 | -76
Build Static Gimbal Mount | Static Fire | Completed | 2025-05-26 | 2025-06-02 | -76
Stage 0 Requirements | Stage 0 | Completed | 2025-06-02 | 2025-06-09 | -69
Stage 0 CAD | Stage 0 | Completed | 2025-06-02 | 2025-06-09 | -69
Stage 0 Build | Stage 0 | Completed | 2025-06-09 | 2025-06-16 | -62
Testing
V2 Mount Protoype 1 Gimbal Test | TVC Mount | Completed | 2025-08-24 | 2025-08-31 | 14
V2 Mount Protoype 2 Gimbal Test | TVC Mount | Completed | 2025-08-31 | 2025-09-07 | 21
Static Fire 1 | TVC Mount | Not Started | 2025-06-09 | 2025-06-13 | -65
Static Fire 2 | TVC Mount | Not Started | 2025-06-16 | 2025-06-20 | -58
Parachute Deploy | RECO | Completed | 2025-06-13 | 2025-06-16 | -62
Flight 1 | Launch | Not Started | 2025-06-21 | 2025-06-22 | -56
Fliht 2 | Launch | Not Started | 2025-07-12 | 2025-07-13 | -35
Formulas:
Legend: = Milestones4352[[#This Row],[End]]-TODAY()

## Dark
PROJECT: Thrust V
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2025-08-17 |  |  |  |  | August | [13 empty] | September | [27 empty] | October
Scrolling increment: | 5 | time axis 2025-08-22 to 2025-10-16
Milestone description | Category | Assigned to | Progress | Start | Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
TVC Mount
Task 1 | Goal | Name | 25% | 2025-08-17 | 3
Task 2 | Milestone |  |  | 2025-08-22 | 1 | bar: F
Task 3 | Low Risk |  | 50% | 2025-08-14 | 10
Task 4 | Milestone |  |  | 2025-09-06 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2025-08-23 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2025-08-23 | 13
Task 2 | On Track |  | 50% | 2025-08-25 | 9
Task 3 | Low Risk |  | 33% | 2025-08-30 | 11
Task 4 | Milestone |  |  | 2025-09-01 | 1 | bar: M
Task 5 |  |  |  | 2025-09-02 | 24
TITLE 3
Task 1 | On Track |  |  | 2025-09-01 | 4
Task 2 | Med Risk |  |  | 2025-09-04 | 14
Task 3 | On Track |  |  | 2025-09-19 | 6
Task 4 | Goal |  |  | 2025-09-23 | 3 | T: 2; W: 2; T: 2
Task 5 | Low Risk |  |  | 2025-08-23 | 19
TITLE 4
Task 1 |  |  |  | 2025-09-26 | 15
Task 2 |  |  |  | 2025-10-10 | 5
Task 3 | Milestone |  |  | 2025-11-21 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2025-08-17 |  |  |  |  | August | [13 empty] | September | [27 empty] | October
Scrolling increment: | 5 | time axis 2025-08-22 to 2025-10-16
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-08-22 to 2025-10-16
TITLE 1
Task 1 | Goal | Name | 25% | 2025-08-17 | 3
Task 2 | Milestone |  |  | 2025-08-22 | 1 | bar: 2025-08-22
Task 3 | Low Risk |  | 50% | 2025-08-14 | 10
Task 4 | Milestone |  |  | 2025-09-06 | 1 | bar: 2025-09-06
Task 5 | Med Risk |  | 10% | 2025-08-23 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2025-08-23 | 13
Task 2 | On Track |  | 50% | 2025-08-25 | 9
Task 3 | Low Risk |  | 33% | 2025-08-30 | 11
Task 4 | Milestone |  |  | 2025-09-01 | 1 | bar: 2025-09-01
Task 5 |  |  |  | 2025-09-02 | 24
TITLE 3
Task 1 | On Track |  |  | 2025-09-01 | 4
Task 2 | Med Risk |  |  | 2025-09-04 | 14
Task 3 | On Track |  |  | 2025-09-19 | 6
Task 4 | Goal |  |  | 2025-09-23 | 3 | 2025-09-23: 2; 2025-09-24: 2; 2025-09-25: 2
Task 5 | Low Risk |  |  | 2025-08-23 | 19
TITLE 4
Task 1 |  |  |  | 2025-09-26 | 15
Task 2 |  |  |  | 2025-10-10 | 5
Task 3 | Milestone |  |  | 2025-11-21 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one